## Sheet1
Issue Type | Epic Name | Summary | Description | Epic Link | Integration/Development/Not needed | Expected Completion Date
Epic | Genaral Display | Critical Care Unit Genaral display areas
Story |  | ICU¦CCU¦PICU dashboard integration and user role base permision |  | Genaral Display |  | 26/07/2018
Story |  | Clinical summary integration |  | Genaral Display |  | 26/07/2018
Story |  | Add a new section for shared reference documents |  | Genaral Display |  | 27/07/2018
Story |  | Add filtering for the "patient visit history" |  | Genaral Display |  | 27/07/2018
Epic | Admission | Critical care unit patient admission
Story |  | View the endorsment documents through ER (acceptance letter, Triage score) |  | Admission |  | 2018-02-07
Story |  | Develop rapid response recored sheet for PICU |  | Admission
Story |  | Develop rapid response recored sheet for ICU |  | Admission
Story |  | Develoment admission / discharge criteria document ICU |  | Admission |  | Done
Story |  | Develoment admission / discharge criteria document CCU |  | Admission |  | Done
Story |  | Develoment admission / discharge criteria document PICU |  | Admission |  | Done
Story |  | Intergrate Interdisciplinary Care Plan |  | Admission |  | 2018-03-07
Story |  | Intergrate doctor order sheet (CPOE/order sets) |  | Admission |  | 2018-04-07
Story |  | Intergrate general orders |  | Admission |  | 2018-05-07
Story |  | Intergrate referrals |  | Admission |  | 2018-06-07
Epic | Initial Assessment | Critical care initial nursing/doctor assessment
Story |  | Integrate arrival setails / allergy |  | Initial Assessment |  | 2018-09-07
Story |  | Integrate vital signs sheet |  | Initial Assessment |  | 2018-10-07
Story |  | Integrate CPOT pain scale |  | Initial Assessment |  | Done
Story |  | Integrate FLACC pain scale |  | Initial Assessment |  | Done
Story |  | Integrate Comfort pain scale |  | Initial Assessment |  | Done
Story |  | Integrate Wong backer pain scale |  | Initial Assessment |  | Done
Story |  | Integrate chief complaint / history |  | Initial Assessment |  | 2018-10-07
Story |  | Integrate screening |  | Initial Assessment |  | 2018-11-07
Story |  | Customize screening for PICU |  | Initial Assessment |  | 2018-11-07
Story |  | Integrate physical Assessment |  | Initial Assessment |  | 2018-11-07
Story |  | Integrate labor and Delivery |  | Initial Assessment |  | 2018-12-07
Story |  | Integrate risk assessment |  | Initial Assessment |  | 2018-12-07
Story |  | Integrate safety check list. |  | Initial Assessment |  | 2018-12-07
Story |  | Integrate discharge planning. |  | Initial Assessment |  | 13/07/2018
Story |  | Integrate VTE |  | Initial Assessment |  | 13/07/2018
Story |  | Integration apache score |  | Initial Assessment |  | 13/07/2018
Story |  | Pediatric nursing assessment |  | Initial Assessment
Epic | Medication | Critical care medication administration
Story |  | Integrate medication administration record |  | Medication |  | 16/07/2018
Story |  | Intergrate prescription |  | Medication |  | 16/07/2018
Epic | Flowsheet | ICU¦CCU¦PICU Flowsheet display
Story |  | Develop generic flowsheet |  | Flowsheet |  | 27/06/2018
Story |  | Develop neuromuscular flow sheet |  | Flowsheet |  | 28/06/2018
Story |  | Develop hemodynamic flow sheet |  | Flowsheet |  | 28/06/2018
Story |  | Develop intake/output flow sheet |  | Flowsheet |  | 29/06/2018
Story |  | Develop renal replacement therapy flow sheet |  | Flowsheet |  | 29/06/2018
Story |  | Develop vital signs flow sheet |  | Flowsheet |  | 29/06/2018
Epic | Daily Assessment
Story |  | Integrate Patient and family education |  | Daily Assessment |  | 17/07/2018
Story |  | Intergrate progress notes |  | Daily Assessment |  | 17/07/2018
Story |  | Intergrate nursing task list |  | Daily Assessment |  | 17/07/2018
Story |  | Intergrate nursing daily reasssesment |  | Daily Assessment |  | 17/07/2018
Story |  | Intergrate IV monitoring sheet |  | Daily Assessment |  | 18/07/2018
Story |  | Interate restraint checklist |  | Daily Assessment |  | 18/07/2018
Story |  | Interate observation flow sheet |  | Daily Assessment |  | 18/07/2018
Story |  | Develop diabetic ketoacidosis monitoring sheet |  | Daily Assessment
Story |  | Develop aniticogulation chart |  | Daily Assessment
Story |  | Integrate diabetic chart |  | Daily Assessment |  | 18/07/2018
Story |  | Integrate insuling sliding scale |  | Daily Assessment |  | 19/07/2018
Story |  | Integrate infiltration/phlebits monitoring sheet |  | Daily Assessment |  | 19/07/2018
Story |  | Integrate IV cannulation check list |  | Daily Assessment |  | 19/07/2018
Story |  | Develop seizure monitoring sheet |  | Daily Assessment |  | 23/07/2018
Story |  | Integrate infection control bundles |  | Daily Assessment |  | 20/07/2018
Epic | Endorsement | Critical care unit doctor/nurse endorsement
Story |  | Integrate doctor shift endorsement |  | Endorsement |  | 20/07/2018
Story |  | Integrate nurse shift endorsement form |  | Endorsement |  | 20/07/2018
Story |  | Integrate SBAR shift endorsement/KARDEX form |  | Endorsement |  | 20/07/2018
Story |  | Integrate unit nursing transfer form |  | Endorsement |  | 23/07/2013
Story |  | Integrate interdepartmental transfer form |  | Endorsement |  | 23/07/2013
Epic | Procedures | ICU¦CCU¦PICU procedures
Story |  | Integrate consents |  | Procedures |  | 23/07/2018
Story |  | Integrate contrast medium questionnaire form |  | Procedures |  | 23/07/2018
Story |  | Integrate minor timeout form |  | Procedures |  | 23/07/2018
Story |  | Integrate OR book preoperative check list |  | Procedures |  | 24/07/2018
Story |  | Integrate CCL book (cathlab) |  | Procedures |  | 24/07/2018
Story |  | Intergrate radiology results |  | Procedures |  | 24/07/2018
Story |  | Develop code bule sheet |  | Procedures
Story |  | Integrate DNR form |  | Procedures |  | 24/07/2018
Story |  | Integrate patient transport Checklist |  | Procedures |  | 24/07/2018
Story |  | Integrate questionnaire for IV contrast medium |  | Procedures |  | 25/07/2018
Story |  | Integrate questionnaire for MRI |  | Procedures |  | 25/07/2018
Story |  | Integrate central line insertion |  | Procedures |  | 25/07/2018
Epic | Wound Management
Story |  | Integrate patient turning chart |  | Wound Management |  | 25/07/2018
Story |  | Integrate formal wound assessment |  | Wound Management |  | 26/07/2018
Story |  | Integrate wound treatment plan |  | Wound Management |  | 26/07/2018
Epic | Blood transfusion
Story |  | Integrate transfusion request |  | Blood transfusion |  | 2018-01-08
Story |  | Integrate blood dispensation |  | Blood transfusion |  | 2018-01-08
Story |  | Integrate blood transfusion monitoring |  | Blood transfusion |  | 2018-01-08
Story |  | Integrate blood transfusion reaction |  | Blood transfusion |  | 2018-02-08
Story |  | Blood bag barcode integration |  | Blood transfusion |  | 2018-02-08
Epic | Discharge
Story |  | Integrate discharge clearance form |  | Discharge |  | 27/07/2018
Story |  | Integrate external transfer form |  | Discharge |  | 27/07/2018
Story |  | Integrate ambulance request |  | Discharge |  | 30/07/2018
Story |  | Integrate discharge summary |  | Discharge |  | 30/07/2018
Story |  | Integrate death notification |  | Discharge |  | 30/07/2018
Story |  | Integrate death certificate |  | Discharge |  | 31/07/2018
Story |  | DAMA integration |  | Discharge |  | 31/07/2018
Story |  | Integrate brain death determination |  | Discharge |  | 31/07/2019
Develoment State
Note Needed
Development
Integraion
| Epic | Expected Completion Date
| Flowsheet | 29/06/2018
| Admission | 2018-06-07
| Initiatial Assessment | 13/07/2018
| Medication | 16/07/2018
| Daily Assessment | 23/07/2018
| Endorsement | 23/07/2013
| Procedure | 25/07/2018
| Wound Management | 26/07/2018
| General Display | 27/07/2018
| Discharge | 31/07/2018
| Blood Transfusion | 2018-02-08